VR PUBLIC SPEAKING TRAINER

Developer Planning Document

Unity • Google Cardboard • Vosk • Android

Virtual classroom + avatar-based audience (no live footage required)

April 2026  •  Sabin

# 1. Project Overview

This document is the authoritative reference for building the VR Public Speaking Trainer from a blank Unity project. It covers architecture, component specs, the full development roadmap, technical decisions, and handoff notes for Claude Code. The virtual classroom approach (procedural environment + humanoid avatars) replaces the original 360° video plan, removing the filming dependency and giving full programmatic control over the audience.

## 1.1 Goal

Build a mobile VR Android application that lets users practice public speaking in a virtual classroom. The system listens to the user's speech in real time, analyzes it along several metrics, and adapts the audience's behaviour accordingly using a rule-based AI model. After each session, the user receives a feedback report.

## 1.2 Key Design Decisions

| DECISION | Virtual classroom + humanoid avatars instead of 360° video. This removes the filming dependency, allows precise control over audience states, and makes the audience system programmatically scriptable from day one. |
| --- | --- |

| DECISION | Offline-first. All processing runs on-device. Vosk handles speech recognition without a network connection. This is a hard requirement given the Android/mobile target. |
| --- | --- |

| DECISION | Rule-based AI (no ML model). The audience adaptation logic is a deterministic rule engine driven by speech metrics. This keeps the system explainable for the research report and the codebase small. |
| --- | --- |

| DECISION | Small codebase target: 8-12 C# scripts. Every script has a single, named responsibility. No monolithic managers. |
| --- | --- |

## 1.3 Tech Stack

| Component | Choice / Notes |
| --- | --- |
| Engine | Unity 6.4 |
| VR SDK | Google Cardboard XR Plugin |
| Speech Recognition | Vosk (offline, on-device) |
| 3D Environment | Unity built-in renderer, URP optional |
| Avatars | Mixamo humanoid rigs (free) or Unity Asset Store |
| Build Target | Android (min API 26 / Android 8.0) |
| Language | C# (.NET Standard 2.1) |
| Version Control | Git (recommended) |

# 2. System Architecture

## 2.1 High-Level Data Flow

The pipeline is linear and unidirectional during a session:

Microphone Input ↓ VoskSpeechRecognizer (transcription) ↓ SpeechAnalyzer (WPM, pauses, filler words) ↓ AudienceRuleEngine (rule evaluation → AudienceState) ↓ AudienceController (avatar animation + audio) ↓ SessionManager (session state, timer) ↓ ResultsUI (end-of-session feedback)

## 2.2 Scene Structure

| Scene | Purpose |
| --- | --- |
| MainMenu | Canvas UI only. Start button launches Session scene. |
| Session | All gameplay. VR camera rig, classroom, avatars, SessionManager. |
| Results | 2D canvas feedback screen shown post-session (or overlay in Session). |

| NOTE | Keep to 2-3 scenes maximum. Avoid scene transitions during a live session to prevent VR discomfort and GC spikes. |
| --- | --- |

## 2.3 GameObject Hierarchy (Session Scene)

Session [Scene Root] ├ CardboardCameraRig │ └ Main Camera (Cardboard head tracking) ├ SessionManager (script) ├ ClassroomEnvironment │ ├ Floor, Walls, Ceiling │ ├ Desks (x20+) │ └ Lighting (baked or mixed) ├ AudienceGroup │ ├ Avatar_00 ... Avatar_N (Animator + AudienceMember script) ├ SpeechSystem │ ├ VoskSpeechRecognizer │ └ SpeechAnalyzer ├ AudienceController ├ AudienceRuleEngine └ UI ├ HUD (timer, live metrics, world-space canvas) └ ResultsPanel (hidden until session end)

# 3. Component Specifications

## 3.1 SessionManager

Central controller for session lifecycle. All other components receive events from this script.

| Property | Details |
| --- | --- |
| Responsibility | Start session, track time, trigger end-of-session, orchestrate component init |
| Key fields | sessionDuration : float, isRunning : bool, currentTime : float |
| Key methods | StartSession(), EndSession(), OnSpeechUpdate(SpeechMetrics) |
| Dependencies | SpeechAnalyzer, AudienceController, ResultsUI |
| Pattern | Singleton (scene-level). Other scripts call SessionManager.Instance. |

## 3.2 VoskSpeechRecognizer

Interfaces with the Vosk library. Handles microphone streaming, feeds audio chunks to Vosk, and fires a C# event with the transcription result.

| Property | Details |
| --- | --- |
| Responsibility | Mic capture, Vosk model loading, real-time transcription |
| Output | OnTranscriptionResult event: (string partialText, bool isFinal) |
| Model | vosk-model-small-en-us (15MB). Bundled in StreamingAssets/VoskModels/ |
| Threading | Vosk runs on a background thread. Unity events marshalled to main thread via a queue. |
| Key risk | Vosk Unity plugin setup. See Stage 4 for integration steps. |

| RISK | The Vosk Unity plugin requires manual .so / .dll placement and may need an AndroidManifest RECORD_AUDIO permission. Allocate extra time at Stage 4. |
| --- | --- |

## 3.3 SpeechAnalyzer

Consumes transcription events and computes the speech quality metrics used by the rule engine.

| Property | Details |
| --- | --- |
| Input | Raw transcription strings (partial + final) from VoskSpeechRecognizer |
| Output | SpeechMetrics struct (WPM, fillerCount, lastPauseDuration, rollingAvgWPM) |
| WPM calculation | Word count over a rolling 10-second window. Recalculated on each final result. |
| Pause detection | Timestamp delta between consecutive final transcription results. >1.5s = pause. |
| Filler words | Configurable list: um, uh, like, you know, basically, literally, etc. |
| Update frequency | Emits SpeechMetrics every 2 seconds to avoid thrashing the rule engine. |

## 3.4 AudienceRuleEngine

Deterministic rule-based evaluator. Takes SpeechMetrics as input and returns an AudienceState enum. This is the 'AI' component of the system.

### Audience States

| State | Avatar Behaviour |
| --- | --- |
| Engaged | Speaker is performing well. Avatars attentive, nodding, eye contact. |
| Neutral | Average performance. Avatars passive, occasionally looking away. |
| Distracted | Low volume or very slow speech. Avatars checking phones, whispering. |
| Restless | Frequent long pauses or filler words. Avatars shifting, fidgeting. |

### Rule Table

| Condition | Triggered State | Notes |
| --- | --- | --- |
| WPM 110-160 AND fillers < 2 in last 30s | Engaged | Optimal speaking range |
| WPM 80-110 OR WPM 160-180 | Neutral | Slightly slow or fast |
| Pause > 3s OR WPM < 80 | Distracted | Low energy detected |
| Pause > 5s OR fillers >= 4 in 30s | Restless | Audience loses patience |
| WPM > 180 sustained 20s | Distracted | Too fast to follow |

| NOTE | Rules are evaluated in priority order (Restless > Distracted > Engaged > Neutral). The engine holds the current state for a minimum of 4 seconds before switching to prevent flickering. |
| --- | --- |

## 3.5 AudienceController

Receives AudienceState from the rule engine and drives avatar animations and ambient audio.

| Property | Details |
| --- | --- |
| Responsibility | Translate AudienceState into Animator parameter changes and audio clips |
| Avatar control | Each avatar has an Animator with a 'State' integer parameter (0=Engaged, 1=Neutral, 2=Distracted, 3=Restless) |
| Randomisation | Not all avatars switch state simultaneously. 30-70% switch on each state change (randomised per avatar), rest catch up over 5s. |
| Audio | Ambient audio layer per state: quiet attentive room / neutral chatter / louder chatter+phones / restless shuffling |
| Transition | CrossFade animations over 0.5s. Audio fades over 1s. |

## 3.6 ClassroomEnvironment

Static procedural classroom. Built in-editor, not at runtime. Build this during Stage 2 before wiring up any scripts.

- Use Unity's ProBuilder (free, included in Package Manager) to create the room geometry

- Desk rows: 5 rows x 4-6 desks = 20-30 audience seats

- Presenter position: centre-front, slight elevation or podium optional

- Lighting: bake a simple directional + ambient. Mixed lighting for mobile performance

- Keep poly count low: target < 50k tris total for the static environment

## 3.7 Avatar Setup

Humanoid avatars using Mixamo rigs (free download at mixamo.com). Required animations per avatar:

| Animation Clip | Description |
| --- | --- |
| Idle_Engaged | Sitting upright, occasional nod, eyes forward |
| Idle_Neutral | Sitting, occasional look away, passive posture |
| Idle_Distracted | Looking at phone (download prop or use animation), slouching |
| Idle_Restless | Shifting in seat, looking around, fidgeting |
| Transition | Crossfade handled by Animator. No explicit transition clips needed. |

| NOTE | Download animations from Mixamo as FBX for Unity, In-Place. Import to Unity and assign to an AnimatorController with a single integer parameter 'State'. Use Any State transitions. |
| --- | --- |

## 3.8 ResultsUI

Displayed after the session ends. Shows a summary of the session metrics and qualitative feedback.

| Metric shown | Display format |
| --- | --- |
| Average WPM | With target range indicator |
| Total filler words | Count + list of which ones |
| Longest pause | Duration in seconds |
| Audience state timeline | Simple bar showing state over time (optional, Stage 9) |
| Overall score | 0-100 weighted engagement score (optional) |
| Tip of the session | One actionable string generated from the worst metric |

# 4. Development Roadmap

Ordered build stages for an intensive 1-2 day coding sprint. Each stage has a single deliverable and must be fully working before moving to the next — the pipeline is strictly sequential. No time boxes; move at your own pace.

## 4.1 Development Workflow

Repeat this loop for every stage:

1 Open Claude Code pointed at your Unity project folder ↓ 2 Give it the current stage deliverable as the task (with planning doc in context) ↓ 3 Claude Code writes / edits C# files directly in your project — review diffs, approve ↓ 4 Switch to Unity Editor — hit Play or build to Android — see what breaks ↓ 5 Paste errors back into Claude Code — it fixes in-context across all affected scripts ↓ 6 Stage deliverable verified → move to next stage

| KEY HABIT | Claude Code holds your whole project in context — it knows SpeechAnalyzer and AudienceRuleEngine simultaneously. Give it one stage at a time, not the full project at once. |
| --- | --- |

## 4.2 Testing Approach

Three testing modes, used at different points in the loop:

| Mode | Speed | Use for |
| --- | --- | --- |
| Unity Editor Play Mode | Instant | 90% of all iteration. Vosk mic input, speech metrics, audience state logic — all work without a device. No Cardboard head tracking, but everything else is testable. |
| Android build to device | 2–5 min build | Head tracking, real VR feel, Cardboard rendering, performance profiling. Do this at the end of each completed stage, not mid-iteration. |
| Unity Remote | ~30 sec | Streams Editor to phone over USB/WiFi. Limited VR support — skip it for this project. |

| PRO TIP | Add a #UNITY_EDITOR preprocessor flag in VoskSpeechRecognizer so it uses the PC mic in Editor mode and the Android mic on device. Speech testing then works instantly in Play Mode without a build — saves hours across the sprint. |
| --- | --- |

## 4.3 Build Stages

Each stage is a discrete deliverable. Complete and verify each before proceeding.

| # | Deliverable | Key Tasks |
| --- | --- | --- |
| 1 | VR Foundation | Install Google Cardboard XR Plugin. Configure build settings for Android. Set up split-screen VR camera rig. Verify head tracking works on device. Create MainMenu + Session scenes. First successful build to phone. |
| 2 | Classroom Environment | Build classroom with ProBuilder (floor, walls, ceiling, desks). Import 3 Mixamo avatars, rig as humanoids, place in scene. Verify target 60fps on device before continuing. |
| 3 | Session System | Write SessionManager: start/stop/timer logic. Add world-space HUD canvas showing timer. Wire up Start button from MainMenu. Session lifecycle events (OnStart, OnEnd) confirmed working. |
| 4 | Vosk Integration | Download Vosk Unity plugin. Bundle small English model in StreamingAssets. Write VoskSpeechRecognizer: mic init, model load, streaming transcription. Debug Android permissions. Display live transcript on HUD. |
| 5 | Speech Metrics | Write SpeechAnalyzer. Implement WPM rolling window, pause detection, filler word counter. Emit SpeechMetrics struct every 2s. Verify metrics appear correctly on HUD in Play Mode. |
| 6 | Rule Engine + Audience AI | Write AudienceRuleEngine with full rule table. Write AudienceController connecting state to Animator parameters. Implement 4s state hold timer. Add ambient audio per state. Test full pipeline end-to-end. |
| 7 | Avatar Animations | Download all 4 animation clips from Mixamo. Set up AnimatorController with Any State transitions on 'State' int. Add randomised per-avatar switch timing in AudienceController. Polish crossfades. |
| 8 | Integration + Hardening | Full end-to-end test: speak for 3 minutes, verify audience responds correctly. Fix metric edge cases. Stress test on device. Address GC spikes or frame drops. Build signed APK. |
| 9 | Results UI + Feedback | Build ResultsPanel. Display all metrics. Implement tip generation logic. Optional: audience state timeline chart. Session save to JSON in persistent storage. |
| 10 | User Study Prep | Recruit 5-10 participants. Define structured session protocol. Prepare quantitative (metrics) and qualitative (questionnaire) data collection. Final build. |

# 5. Script Index

All 10 scripts. Each has a single responsibility. No script should exceed ~200 lines.

| Script | Responsibility |
| --- | --- |
| SessionManager.cs | Session lifecycle: start, stop, timer, event dispatch |
| VoskSpeechRecognizer.cs | Mic input, Vosk model loading, streaming transcription |
| SpeechAnalyzer.cs | WPM, pause duration, filler word counting; emits SpeechMetrics |
| AudienceRuleEngine.cs | Rule evaluation: SpeechMetrics -> AudienceState enum |
| AudienceController.cs | Avatar Animator control + ambient audio per AudienceState |
| AudienceMember.cs | Per-avatar component: holds individual state, handles crossfade timing |
| ClassroomBuilder.cs | Editor-only helper (optional): procedural desk placement |
| HUDController.cs | Updates world-space HUD: timer, WPM, pause count, current audience state |
| ResultsUI.cs | Renders end-of-session metrics panel; generates tip string |
| SpeechMetrics.cs | Shared struct/data class. No logic. Passed between components. |

# 6. Risks & Mitigations

| Risk | Severity | Mitigation |
| --- | --- | --- |
| Vosk Unity plugin integration fails or crashes on Android | HIGH | Test Vosk in isolation at Stage 4 before depending on it. Have a fallback: Unity Microphone API with manual word counting from partial audio (no NLP). |
| Frame rate drops below 60fps on target device | MED | Bake lighting. Keep avatar count to 20. Use LODs. Profile at the end of Stage 2 before adding avatars. |
| Google Cardboard tracking is insufficient / uncomfortable | MED | Test on multiple devices at Stage 1. Cardboard is low-latency by design but varies per phone. |
| SpeechAnalyzer metrics are inaccurate | MED | Unit test SpeechAnalyzer with pre-recorded transcripts. Allow threshold tuning via Inspector fields. |
| Audience state transitions feel jarring | LOW | Implement 4s hold timer. Randomise per-avatar switch timing. Use animation crossfade. |
| Masters schedule conflicts delay development | LOW | The roadmap front-loads infrastructure. Stages 8-10 have more slack for catch-up. |

# 7. Claude Code Handoff Notes

Instructions for picking this project up in Claude Code with a blank Unity project.

## 7.1 Unity Project Setup

- Unity version: 6.4

- Add via Package Manager: Google Cardboard XR Plugin, ProBuilder, TextMeshPro

- Build Settings: switch to Android. Min API Level 26. IL2CPP scripting backend. ARM64 target.

- Player Settings: enable Vulkan (primary) + OpenGLES3 (fallback). Disable unnecessary permissions.

- XR Plug-in Management: enable Cardboard under Android tab.

## 7.2 Vosk Setup

- Download vosk-unity-plugin from the Vosk GitHub (alphacep/vosk-api)

- Copy Plugins/Android/ .so files to Assets/Plugins/Android/

- Download vosk-model-small-en-us-0.15 and place in Assets/StreamingAssets/VoskModels/

- Add RECORD_AUDIO to AndroidManifest.xml under Plugins/Android/

- Initialise with: Model model = new Model(Application.streamingAssetsPath + "/VoskModels/vosk-model-small-en-us-0.15")

## 7.3 Mixamo Assets

- Go to mixamo.com. Sign in with Adobe account (free).

- Search character: Y Bot or X Bot (generic humanoid, no clothing issues)

- Download 4 animations: Sitting Idle, Sitting Looking Around, Sitting Typing (phone proxy), Sitting Fidget

- Download format: FBX for Unity, In Place, 30fps

- Import to Assets/Animations/. Configure as Humanoid rig in Import Settings.

## 7.4 Starting Prompt for Claude Code

Suggested opening prompt: "I have a blank Unity 6.4 project for a VR public speaking trainer app targeting Android with Google Cardboard. I have a planning document that defines the architecture, all 10 scripts, the rule-based AI audience system, and the build stages. Let's start with Stage 1: setting up the Cardboard XR camera rig, configuring build settings, and creating the MainMenu and Session scenes. Please generate the initial project structure and any required scripts for this stage."

## 7.5 Key Constraints to Re-state in Claude Code

- Offline only — no network calls at runtime

- 8-12 scripts maximum — do not split logic unnecessarily

- Rule engine must be explainable — no ML models, no black boxes

- Android target — test on device at the end of each completed stage, not just in Editor

- No third-party paid assets — Unity built-ins, ProBuilder, Mixamo (free), Vosk (MIT)

# Appendix: Useful References

| Resource | URL / Location |
| --- | --- |
| Google Cardboard Unity | developers.google.com/cardboard/develop/unity/quickstart |
| Vosk Unity Plugin | github.com/alphacep/vosk-api (Unity samples in samples/unity) |
| Mixamo | mixamo.com (free Humanoid animations + characters) |
| ProBuilder docs | docs.unity3d.com/Packages/com.unity.probuilder |
| Android Build Guide | docs.unity3d.com/Manual/android-getting-started |
| Vosk Models | alphacephei.com/vosk/models (use vosk-model-small-en-us-0.15) |

End of Document  •  VR Public Speaking Trainer  •  April 2026